## Product Backlog
STORY_ID | USER_STORY | AS_A/AN | I_WANT_TO... | SO_THAT... | PRIORITY | EFFORT | ITEM_ID | DESCRIPTION | NOTES/COMMENTS | STATUS | DEFINITION_OF_DONE | DoD Status
0 | Logging in | User | log in | I can access the service | HIGH | 3 | 0.1 | Create API for logging in |  | DONE | Final design of product confirmed/accepted by product owner and client | FALSE
[7 empty] | 0.2 | Create a database to store login information |  | DONE | All code refactored to consistency | FALSE
[11 empty] | End-user documentation ready | FALSE
1 | Logging in as a customer | customer | login to the online application | I can use the online services and veiw my Dashboard | HIGH | 2 | 1.1 | Log in with customer details |  | DONE | All unit tests written and passed | FALSE
1.2
[7 empty] | 1.3 | Dashboard Home |  | DONE | All services displayed correctly as Card Components | FALSE
[7 empty] | 1.4 | Card Componets for Services offered |  | DONE | Card Component displays sercie being offered with an image, title and description. Renders correctly and passes unit tests.
[7 empty] | 1.5 | Booking page for a service |  | IN SPRINT
[7 empty] | 1.6 | Navigation - Header / Side bar |  | DONE | Header Bar/ Side Bar and Navigation reviewed and given final O.K | FALSE
[7 empty] | 1.7 | Login / Logout |  | IN SPRINT |  | FALSE
FALSE
2 | Logging in as an admin | admin | log into my admin account | I can see my dashboard with any important updates | HIGH | 2 | 2.1 | Log in with admin details |  | DONE | All To-Do's are completed in management board | FALSE
[7 empty] | 2.2 | Display dashboard with overview details and links to specific actions |  | TO DO | All outstanding issues are resolved | FALSE
[11 empty] | Product is a deployable release | FALSE
3 | Logging in as a worker | worker | log into my worker account | I can view my dashboard and manage relevant bookings | HIGH | 2 | 3.1 | Log in with worker details |  | DONE
[7 empty] | 3.2 | Display dashboard displaying jobs specific to worker |  | TO DO
4 | View 'About' information | customer | view the details of the company on the "about" section of the home page | I can better understand the services provided by the organisation | LOW | 1 | 4.1 | Clickable link to an 'About' page |  | DONE
[7 empty] | 4.2 | Page displaying information about the AGME service |  | IN SPRINT
5 | View contact details | customer | view the contact details of the company on the "contact section of the home page | I can find out the contact details of the company (phone, email etc,) | LOW | 1 | 5.1 | Clickable link leading to a contact page |  | IN SPRINT
[7 empty] | 5.2 | Display contact page for ways to communicate with service |  | IN SPRINT
6 | Customer signs up | new customer | be able to sign up to the application | I can make booking appointments for services | MEDIUM | 3 | 6.1 | Link to registration as a new customer |  | DONE
[7 empty] | 6.2 | Form for entering details of new customer |  | DONE
[7 empty] | 6.3 | Data of new customer saved to server |  | DONE
[7 empty] | 6.4 | Redirect to customer dashboard customer account after registration |  | IN SPRINT
7 | Admin modifies available times | admin | be able to modify the available times for a public holiday | customers can see that the available times are for that specific day | LOW | 5 | 7.1 | Selectable option to view a calender | SUBJECT TO CHANGE | TO DO
[7 empty] | 7.2 | Calender displays days with available times and unavailable times | SUBJECT TO CHANGE | TO DO
[7 empty] | 7.3 | Changed dates updated and saved into server | SUBJECT TO CHANGE | TO DO
8 | Admin adding new dates for bookings | admin | add in new calender dates | more dates are available for new bookings | MEDIUM | 5 | 8.1 | Select dates from a list/calender or manually input dates in |  | TO DO
[7 empty] | 8.2 | New selected dates should be able to be available for booking |  | TO DO
9 | Admin checking work roster | admin | click on a roster option | I can view the rostered workers for the next 7 days | MEDIUM | 3 | 9.1 | Select link to review rostered workers |  | TO DO
[7 empty] | 9.2 | Display a list of workers rostered to work for the next 7 days |  | TO DO
10 | Admin views the summary of past bookings | admin | view the summary of past bookings | I can answer any customer queries regarding their previous bookings | LOW | 2 | 10.1 | Select option to view a list of past bookings |  | TO DO
[7 empty] | 10.2 | Display list of bookings and their history e.g. completed, cancelled etc. |  | TO DO
[7 empty] | 10.3 | Select a booking and display details of that booking |  | TO DO
11 | Admin makes adjustments to any existing bookings | admin | manually adjust an existing bookings | I can make modifications to any customer queries that has escalated due to certain circumstances | LOW | 2 | 11.1 | Option to manually change booking details |  | TO DO
[7 empty] | 11.2 | Booking details reflected in customer view |  | TO DO
12 | Admin adds a new worker | admin | add a new worker/employee | I can have them operate and make the booking service more efficient | HIGH | 3 | 12.1 | Selectable option to add a new worker/employee |  | TO DO
[7 empty] | 12.2 | Display page with forms to enter new worker/employee details |  | TO DO
[7 empty] | 12.3 | New worker/employee details are saved into database |  | TO DO
13 | Admin edits a current worker | admin | edit a current worker/employee's details | I can correct or update their information to maintain accuracy | MEDIUM | 2 | 13.1 | Selectable option to update employee details |  | TO DO
[7 empty] | 13.2 | Display page and form to update worker/employee details |  | TO DO
[7 empty] | 13.3 | Updated worker/employee details are saved to database |  | TO DO
14 | Admin views worker availabilities | admin | view all worker/employee availabilities for the next 7 days | I can schedule my employees efficiently according to their availability | LOW | 5 | 14.1 | Selectable option to display worker availabilities |  | TO DO
[7 empty] | 14.2 | Display view of workers that are allocated to work |  | TO DO
15 | Admin deletes worker account | admin | be able to delete a user/worker account | false and spam bookings can be deterred | LOW | 1 | 15.1 | Selectable option to remove a worker from the roster |  | TO DO
[7 empty] | 15.2 | Display list of all worker | The worker can be selected from the list | TO DO
[7 empty] | 15.3 | Worker deleted from database | Worker can be completely removed or moved to a 'deleted' database | TO DO
16 | Customer books a certain worker | customer | select a worker | my booking is maintained/serviced by the specific worker | MEDIUM | 5 | 16.1 | Option to select a specific worker when booking a service |  | DONE
[7 empty] | 16.2 | Selected worker is entered into the booking details |  | DONE
17 | Customer checks available dates | customer | check certain dates | I can complete a booking | MEDIUM | 4 | 17.1 | List of available dates for booking service are displayed creating a new booking |  | IN SPRINT
18 | Customer books a service for a date/time | customer | book a specific service for a day/time and a worker | I can recieve said service to suit my needs | HIGH | 5 | 18.1 | Display a list of available services when a date is selected |  | IN SPRINT
[7 empty] | 18.2 | Display a list of workers available when a date and service is selected |  | IN SPRINT
[7 empty] | 18.3 | Selectable options for both services and workers |  | TO DO
[7 empty] | 18.4 | Services and worker options are saved to booking details |  | IN SPRINT
19 | Customer updates contact details | customer | update my contact details | if anything goes wrong i can be informed | LOW | 2 | 19.1 | Selectable to update contact details page |  | TO DO
[7 empty] | 19.2 | Display page with form to update contact details |  | TO DO
[7 empty] | 19.3 | New contact details saved to database |  | TO DO
20 | Customer views personal account details | customer | be able to view my account details | I can make sure that all of my data are correct | MEDIUM | 2 | 20.1 | Selectable option to account information page |  | TO DO
[7 empty] | 20.2 | Dispaly page with customer details listed |  | DONE
21 | Customer edits contact number | customer | edit my contact number | my contact details are up to date | LOW | 1 | 21.1 | Form input to enter new/updated contact number and save button |  | TO DO
[7 empty] | 21.2 | Contact number saved to database |  | DONE
22 | Customer edits address | customer | edit my address | my address details are up to date | LOW | 1 | 22.1 | Form input to enter new/updated address details and save button |  | TO DO
[7 empty] | 22.2 | New address saved to database |  | DONE
23 | Customer edits their information | customer | edit my account details | I can correct or update information about myself | LOW | 2 | 23.1 | Form input to modify account information |  | TO DO
[7 empty] | 23.2 | New account information updated to the database |  | DONE
24 | Customer cancels booking | customer | cancel a booking | I can rebook another time | MEDIUM | 2 | 24.1 | Selectable option to cancel booking shown in the booking details page |  | TO DO
[7 empty] | 24.2 | Booking is removed from the database |  | TO DO
25 | Customer unable to cancel booking | customer | not be able to cancel a booking | I am informed why it does not cancel | MEDIUM | 2 | 25.1 | Booking is not removed and pop message informs customer booking has not been cancelled |  | TO DO
26 | Customer checking latest booking | customer | see my latest booking | I know what time my booking starts | LOW | 2 | 26.1 | Selectable option to view list of bookings |  | TO DO
[7 empty] | 26.2 | Bookings displayed in list a re selectable |  | TO DO
[7 empty] | 26.3 | Booking details are shown when booking is selected from the list |  | TO DO
27 | Customer views booking history | customer | view all my previous bookings that I have made | I can refer to any previous bookins when I contact the staff | MEDIUM | 3 | 27.1 | Selectable option to view a list of previous bookings |  | IN SPRINT
[7 empty] | 27.2 | Display page with list of previous bookings |  | IN SPRINT
[7 empty] | 27.3 | Previous booking details are shown when selected from the list |  | TO DO
28 | Worker viewing work order | worker | be able to view assigned duties and other details | I can organise my time suitably | MEDIUM | 4 | 28.1 | Display list of work duties on the worker dashboard |  | IN SPRINT
29 | Worker views their profile | worker | view my account details | I can look at what data I have provided | MEDIUM | 2 | 29.1 | Selectable option to view personal details |  | IN SPRINT
[7 empty] | 29.2 | Personal details are displayed when option is selected |  | IN SPRINT

## Sprint 1 Backlog
PBI_ID | USER_STORY | ITEM_ID | DESCRIPTION | ASSIGNED_TO | STATUS | ESTIMATED_EFFORT (HOURS) |  | DAY_0 | DAY_1 | DAY_2 | DAY_3 | DAY_4 | DAY_5 | DAY_6 | DAY_7 | DAY_8 | DAY_9 | DAY_10 | DAY_11 | DAY_12 | DAY_13 | DAY_14
0 | Logging in | 0.1 | Create API for logging in | Alan | 2020-03-01 | 3 | Total Effort | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
|  | 0.2 | Create database to store login information | Alan | DONE | 2 | Velocity | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
[7 empty] | Remaining Effort (Hours) | 56 | 54 | 54 | 53 | 53 | 53 | 53 | 52 | 52 | 51 | 51 | 51 | 51 | 51 | 51
1 | Logging in as a customer | 1.1 | Log in with customer details | Matthew | TO DO | 3 | Completed Effort (Hours) | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 5 | 0 | 0 | 0 | 0 | 0
|  | 1.2 | Display customer dashboard with available links | Gav | 2020-06-01 | 6 | Remaining Tasks | 19 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
[7 empty] | Completed Tasks | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Logging in as an admin | 2.1 | Log in with admin details | Youssef | TO DO | 2 | Ideal Burndown | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
|  | 2.2 | Display dashboard with overview details and links to specific actions | Hamed | TO DO | 5
3 | Logging in as a worker | 3.1 | Log in with worker details | Youssef | TO DO | 2
|  | 3.2 | Display dashboard displaying jobs specific to worker | Gav | TO DO | 4
4 | View 'About' information | 4.1 | Clickable link to an 'About' page | Matthew | 2020-02-01 | 2
|  | 4.2 | Page displaying information about the service | Alan | TO DO | 2
5 | View contact details | 5.1 | Clickable link leading to a contact page | Matthew | TO DO | 2
|  | 5.2 | Display contact page for ways to communicate with service | Gav | TO DO | 2
6 | Customer signs up | 6.1 | Link to registration as a new customer | Matthew | TO DO | 2
|  | 6.2 | Form for entering details of new customer | Matthew | TO DO | 3
|  | 6.3 | Data of new customer saved to server | Alan | TO DO | 3
|  | 6.4 | Redirect to customer dashboard customer account after registration | Hamed | TO DO | 2
12 | Admin adds a new worker | 12.1 | Selectable option to add a new worker/employee | Hamed | TO DO | 3
|  | 12.2 | Display page with forms to enter new worker/employee details | Gav | TO DO | 5
|  | 12.3 | New worker/employee details are saved into database | Alan | TO DO | 3
[5 empty] | Total Effort | 56

## Sprint 2 Backlog
PBI_ID | USER_STORY | ITEM_ID | DESCRIPTION | ASSIGNED_TO | STATUS | ESTIMATED_EFFORT (HOURS) |  | DAY_0 | DAY_1 | DAY_2 | DAY_3 | DAY_4 | DAY_5 | DAY_6 | DAY_7 | DAY_8 | DAY_9 | DAY_10 | DAY_11 | DAY_12 | DAY_13 | DAY_14
0 | Logging in | 0.1 | Create API for logging in | Alan | DONE | 3 | Total Effort | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[7 empty] | Velocity | 0 | 0 | 0 | 2 | 2 | 1 | 3 | 1 | 2 | 5 | 2 | 4 | 2 | 2 | 3
1 | Logging in as a customer | 1.1 | Log in with customer details | Matthew | DONE | 3 | Remaining Effort (Hours) | 54 | 54 | 54 | 52 | 50 | 49 | 46 | 45 | 43 | 38 | 36 | 32 | 30 | 28 | 25
|  | 1.2 | Display customer dashboard with available links | Gav | 2020-06-01 | 6 | Completed Effort (Hours) | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 7 | 0 | 8 | 11 | 14 | 16 | 0
[7 empty] | Remaining Tasks | 18 | 18 | 18 | 18 | 18 | 17 | 16 | 16 | 15 | 13 | 12 | 11 | 10 | 9 | 9
2 | Logging in as an admin | 2.1 | Log in with admin details | Matthew | DONE | 2 | Completed Tasks | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 1 | 1 | 1 | 0
|  | 2.2 | Display dashboard with overview details and links to specific actions | Hamed | TO DO | 5 | Ideal Burndown | 54 | 50.1429 | 46.2857 | 42.4286 | 38.5714 | 34.7143 | 30.8571 | 27 | 23.1429 | 19.2857 | 15.4286 | 11.5714 | 7.7143 | 3.8571 | 0
3 | Logging in as a worker | 3.1 | Log in with worker details | Youssef | DONE | 2
|  | 3.2 | Display dashboard displaying jobs specific to worker | Gav | TO DO | 4
4 | View 'About' information | 4.1 | Clickable link to an 'About' page | Matthew | DONE | 2
|  | 4.2 | Page displaying information about the service | Alan | TO DO | 2
5 | View contact details | 5.1 | Clickable link leading to a contact page | Matthew | DONE | 2
|  | 5.2 | Display contact page for ways to communicate with service | Gav | TO DO | 2
6 | Customer signs up | 6.1 | Link to registration as a new customer | Gav | DONE | 2
|  | 6.2 | Form for entering details of new customer | Matthew | DONE | 3
|  | 6.3 | Data of new customer saved to server | Alan | DONE | 3
|  | 6.4 | Redirect to customer dashboard customer account after registration | Alan | 2020-02-01 | 2
12 | Admin adds a new worker | 12.1 | Selectable option to add a new worker/employee | Hamed | TO DO | 3
|  | 12.2 | Display page with forms to enter new worker/employee details | Gav | TO DO | 5
|  | 12.3 | New worker/employee details are saved into database | Alan | TO DO | 3
[5 empty] | Total Effort | 54
[5 empty] | Total Effort | 54

## Sprint 3 Backlog
PBI_ID | USER_STORY | ITEM_ID | DESCRIPTION | ASSIGNED_TO | STATUS | ESTIMATED_EFFORT (HOURS) |  | DAY_0 | DAY_1 | DAY_2 | DAY_3 | DAY_4 | DAY_5 | DAY_6 | DAY_7 | DAY_8 | DAY_9 | DAY_10 | DAY_11 | DAY_12 | DAY_13 | DAY_14
1 | Logging in as a customer | 1.2 | Display customer dashboard with available links | Gav | 2020-06-03 | 10 | Total Effort | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
[7 empty] | Velocity | 2 | 4 | 3 | 3 | 2 | 3 | 3 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0
4 | View 'About' information | 4.2 | Page displaying information about the service | Hamed | TO DO | 2 | Remaining Effort (Hours) | 48 | 44 | 41 | 38 | 36 | 33 | 30 | 27 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[7 empty] | Completed Effort (Hours) | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 12 | 20 | 20 | 20 | 20 | 20 | 20 | 20
5 | View contact details | 5.2 | Display contact page for ways to communicate with service | Gav | TO DO | 2 | Remaining Tasks | 11 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
[7 empty] | Completed Tasks | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
20 | Customer views personal account details | 20.2 | Dispaly page with customer details listed | Gav | TO DO | 2 | Ideal Burndown | 48 | 44.5714 | 41.1429 | 37.7143 | 34.2857 | 30.8571 | 27.4286 | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0
21 | Customer edits contact number | 21.2 | Contact number saved to database | Matt | DONE | 2
22 | Customer edits address | 22.2 | New address saved to database | Matt | DONE | 2
23 | Customer edits their information | 23.2 | New account information updated to the database | Matt | DONE | 2
16 | Customer books a certain worker | 16.1 | Option to select a specific worker when booking a service | Alan | DONE | 8
|  | 16.2 | Selected worker is entered into the booking details | Matt/Alan | DONE | 6
17 | Customer checks available dates | 17.1 | List of available dates for booking service are displayed creating a new booking | Matt | TO DO | 8
18 | Customer books a service for a date/time | 18.1 | Display a list of available services when a date is selected | Matt | TO DO | 8
[5 empty] | Total Effort | 52
[5 empty] | Total Effort | 104

## Sprint 4 Backlog
PBI_ID | USER_STORY | ITEM_ID | DESCRIPTION | ASSIGNED_TO | STATUS | ESTIMATED_EFFORT (HOURS) |  | DAY_0 | DAY_1 | DAY_2 | DAY_3 | DAY_4 | DAY_5 | DAY_6 | DAY_7 | DAY_8 | DAY_9 | DAY_10 | DAY_11 | DAY_12 | DAY_13 | DAY_14 | DAY_15 | DAY_16
1 | Logging in as a customer | 1.3 | Dashboard Home | Gav | DONE | 4 | Total Effort | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
|  | 1.4 | Card Componets for Services offered | Gav | DONE | 2 | Velocity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.5 | Booking page for a service | Gav | DONE | 4 | Remaining Effort (Hours) | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
|  | 1.6 | Navigation - Header / Side bar | Hamed | DONE | 2 | Completed Effort (Hours) | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | 1.7 | Login / Logout | Gav | DONE
[7 empty] | Remaining Tasks | 16 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
4 | View 'About' information | 4.2 | Page displaying information about the AGME service | Hamed | DONE | 2 | Completed Tasks | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Ideal Burndown | 72 | 67.5 | 63 | 58.5 | 54 | 49.5 | 45 | 40.5 | 36 | 31.5 | 27 | 22.5 | 18 | 13.5 | 9 | 4.5 | 0
5 | View contact details | 5.2 | Display contact page for ways to communicate with service | Hamed | DONE | 3
20 | Customer views personal account details | 20.2 | Dispaly page with customer details listed | Gav | TO DO | 3
28 | Worker viewing work order | 28.1 | Display list of work duties on the worker dashboard | Hamed | TO DO | 3
29 | Worker views their profile | 29.1 | Selectable option to view personal details | Matt | TO DO | 6
|  | 29.2 | Personal details are displayed when option is selected | Alan | TO DO | 6
27 | Customer views booking history | 27.1 | Selectable option to view a list of previous bookings | Alan | TO DO | 5
|  | 27.2 | Display page with list of previous bookings | Alan | TO DO | 5
|  | 27.3 | Previous booking details are shown when selected from the list | Alan | TO DO | 5
18 | Customer books a service for a date/time | 18.1 | Display a list of available services when a date is selected | Matt | TO DO | 8
|  | 18.2 | Display a list of workers available when a date and service is selected | Matt | TO DO | 8
|  | 18.4 | Services and worker options are saved to booking details | Matt | TO DO | 6
[5 empty] | Total Effort | 72